## Risk List
Project title: Optical Character Recognition system for billet identification
| Title or short description of the risk | Detailed description of the risk and comments | Person or Organisation that is responsible for this risk resp. who will perform the defined actions | Category of the risk: Implementation Management Market Projectmanagement Research Technical Other | Description how you know the risk occured | Probability of occurence of the Risk: Show scale | Impact: Levels of consequence | Is calculated automatically |  |  | Preventive action to mitigate the probability | Corrective action to reduce the resulting damage | Describes how we will know that this risk is successfully mitigated. | Probability after application of measures: Show scale | Impact after application of measures |  |  | Is calculated automatically
ID | Title | Description | Responsible | Category | Indicators of occurence | Probability | Impact | Risk score | Impact x-axis | Likelihood y-axis | Preventive Measure | Corrective Measure | Success factors | Probability ' | Impact ' | Impact x-axis | Likelihood y-axis | Risk score '
R1 | Inadequate Hardware specifications | Refers to the risk associated with incomplete or insufficient validation of hardware specifications during the design phase. This could result in uncertainties, potential conflicts, and the need for significant redesign during the hardware development phase, impacting the project timeline and budget. | Research Partner Representative/ Technical team (CSEM) | Research | Insufficient validation of specifications during design phase | Possible | Major | 12 | 3.5 | 2.5 | Regular design reviews with stakeholders | Modify specifications based on feedback | Timely identification and Correction of design issues | Unlikely | Major | 3.5 | 1.5 | 8
R2 | Camera malfunction during data collection | Refers to the risk of unexpected errors, such as hardware malfunctions or software glitches, occurring during image capture sessions. These errors could manifest as disruptions in image capture, anomalies in image quality, or inconsistent timestamps in the collected data. | Technical Team/ Auxiliary Staff (SMS Concast) | Technical | Unexpected errors during image capture sessions | Possible | Moderate | 9 | 2.5 | 2.5 | Implement redundant camera systems/ Check regularly camera output | Use backup from redundant systems | Accurate and complete dataset even in the presence of hardware failure | Possible | Moderate | 2.5 | 2.5 | 9
R3 | Incorrect or not precise enough labeling | Refers to the risk of inconsistencies or inaccuracies in the labeled dataset. It emphasizes potential causes such as human errors, unclear guidelines, or inadequate training, and outlines indicators to detect the occurrence of this risk. | Technical Team/ Auxiliary Staff (SMS Concast) | Implementation | Inconsistencies or inaccuracies in labeled dataset | Unlikely | Critical | 10 | 4.5 | 1.5 | Develop clear labeling guidelines and povide training for labelers | Implement a review process for labeled data | Enhanced precision in OCR algorithm training data | Unlikely | Critical | 4.5 | 1.5 | 10
R4 | Overfitting during OCR algorithm training | Refers to the risk of the model learning the training data too well, resulting in poor generalization to new, unseen data. It outlines indicators of overfitting, such as excessively high accuracy on the training data but lower performance on real-world examples. | Data Analysis experts (CSEM) | Technical | Poor generalization to real world scenario (WP5) | Likely | Major | 16 | 3.5 | 3.5 | Implement cross-validation techniques during model training | Retrain the model on a more diverse dataset | Improved OCR performance on varied inputs | Likely | Major | 3.5 | 3.5 | 16
R5 | Delays in project timeline | Refers to the risk of not adhering to the project plan, resulting in delays and potential cost overruns. It outlines indicators of occurrence, such as missed milestones or deviations from the planned schedule. | Project Manager | Management | Failure to adhere to the project plan | Likely | Minor | 8 | 1.5 | 3.5 | Regular monitoring of project activities, timelines and milestones | Implement fast-tracking or resource reallocation | Project completion within the planned timeframe | Possible | Minor | 1.5 | 2.5 | 6
R6 | [8 empty] | -1 | -1 | [5 empty] | -1 | -1
R7 | [8 empty] | -1 | -1 | [5 empty] | -1 | -1
R8 | [8 empty] | -1 | -1 | [5 empty] | -1 | -1
R9 | [8 empty] | -1 | -1 | [5 empty] | -1 | -1
R10 | [8 empty] | -1 | -1 | [5 empty] | -1 | -1
R11 | [8 empty] | -1 | -1 | [5 empty] | -1 | -1
R12 | [8 empty] | -1 | -1 | [5 empty] | -1 | -1
R13 | [8 empty] | -1 | -1 | [5 empty] | -1 | -1
R14 | [8 empty] | -1 | -1 | [5 empty] | -1 | -1
R15 | [8 empty] | -1 | -1 | [5 empty] | -1 | -1
R16 | [8 empty] | -1 | -1 | [5 empty] | -1 | -1
R17 | [8 empty] | -1 | -1 | [5 empty] | -1 | -1
R18 | [8 empty] | -1 | -1 | [5 empty] | -1 | -1
R19 | [8 empty] | -1 | -1 | [5 empty] | -1 | -1
R20 | [8 empty] | -1 | -1 | [5 empty] | -1 | -1
R21 | [8 empty] | -1 | -1 | [5 empty] | -1 | -1
R22 | [8 empty] | -1 | -1 | [5 empty] | -1 | -1
R23 | [8 empty] | -1 | -1 | [5 empty] | -1 | -1
R24 | [8 empty] | -1 | -1 | [5 empty] | -1 | -1
R25 | [8 empty] | -1 | -1 | [5 empty] | -1 | -1
R26 | [8 empty] | -1 | -1 | [5 empty] | -1 | -1
R27 | [8 empty] | -1 | -1 | [5 empty] | -1 | -1
R28 | [8 empty] | -1 | -1 | [5 empty] | -1 | -1
R29 | [8 empty] | -1 | -1 | [5 empty] | -1 | -1
R30 | [8 empty] | -1 | -1 | [5 empty] | -1 | -1
R31 | [8 empty] | -1 | -1 | [5 empty] | -1 | -1
R32 | [8 empty] | -1 | -1 | [5 empty] | -1 | -1
R33 | [8 empty] | -1 | -1 | [5 empty] | -1 | -1
R34 | [8 empty] | -1 | -1 | [5 empty] | -1 | -1
R35 | [8 empty] | -1 | -1 | [5 empty] | -1 | -1
R36 | [8 empty] | -1 | -1 | [5 empty] | -1 | -1
R37 | [8 empty] | -1 | -1 | [5 empty] | -1 | -1
R38 | [8 empty] | -1 | -1 | [5 empty] | -1 | -1
R39 | [8 empty] | -1 | -1 | [5 empty] | -1 | -1
R40 | [8 empty] | -1 | -1 | [5 empty] | -1 | -1
R41 | [8 empty] | -1 | -1 | [5 empty] | -1 | -1
R42 | [8 empty] | -1 | -1 | [5 empty] | -1 | -1
R43 | [8 empty] | -1 | -1 | [5 empty] | -1 | -1
R44 | [8 empty] | -1 | -1 | [5 empty] | -1 | -1
R45 | [8 empty] | -1 | -1 | [5 empty] | -1 | -1
R46 | [8 empty] | -1 | -1 | [5 empty] | -1 | -1
R47 | [8 empty] | -1 | -1 | [5 empty] | -1 | -1
R48 | [8 empty] | -1 | -1 | [5 empty] | -1 | -1
R49 | [8 empty] | -1 | -1 | [5 empty] | -1 | -1
R50 | [8 empty] | -1 | -1 | [5 empty] | -1 | -1
Note on B3: Titel or short description of the risk
Note on C3: Detailes description of the risk and comments can be made here
Note on D3: Person or Organisation that is responsible for this risk resp. who will perform the defined actions
Note on E3: Category of the risk
Note on F3: How do you know the risk occured?
Note on G3: Probability of occurence of the risk: Remote: Probability of less than 10%. Unlikely: Probability between 10% and 35% Possible: Probability between 36% to 64%. Likely: Probability 65% to 90%. Certain: Probability above 90%.
Note on H3: Levels of consequence: Insignificant: Easily handled within the normal course of operations with no additional costs Minor: Some disruption within the normal functions. Manageable risk with minimum estimated cost Moderate: Immediate time/resource reallocation will be necessary with a moderate estimated cost Major: Operations are severely disrupted and significant risk of failure to part of the business is possible Critical: Significant going concerns exists with the business and the risk is classified as critical
Note on I3: Is calculated automatically (Probability * Impact)
Note on L3: Preventive action to mitigate the probability Example Risk: Building burning Measure: Build non smoking areas in critical areas.
Note on M3: Corrective action to reduce the resulting damage Example Risk: Building burning Measure: Build sprinkler systems and provide emergency exits and escape routes.
Note on N3: How will we know that this risk is successfully mitigated? Example Risk: Increase of budget Success factor: Tracking of costs and closing the project in budget
Note on O3: Probability after application of measures
Note on P3: Impact after application of measures
Note on S3: Risk score after application of measures Is calculated automatically (Probability' * Impact')

## Parameter
Probability
Remote | 1 | Probability of less than 10%.
Unlikely | 2 | Probability between 10% and 35%
Possible | 3 | Probability between 36% to 64%.
Likely | 4 | Probability 65% to 90%.
Certain | 5 | Probability above 90%.
Impact
Insignificant | 1 | Easily handled within the normal course of operations with no additional costs
Minor | 2 | Some disruption within the normal functions. Manageable risk with minimum estimated cost
Moderate | 3 | Immediate time/resource reallocation will be necessary with a moderate estimated cost
Major | 4 | Operations are severely disrupted and significant risk of failure to part of the business is possible
Critical | 5 | Significant going concerns exists with the business and the risk is classified as critical
Category
Implementation | 1
Management | 2
Market | 3
Projectmanagement | 4
Research | 5
Technical | 6
Other | 7

## Chart Template
|  | Risks | [6 empty] | Risks after measures
| Certain | Low Med | Medium | Med Hi | High | High |  | Certain | Low Med | Medium | Med Hi | High | High
Likelihood | Likely | Low | Low Med | Medium | Med Hi | High | Likelihood | Likely | Low | Low Med | Medium | Med Hi | High
| Possible | Low | Low Med | Medium | Med Hi | Med Hi |  | Possible | Low | Low Med | Medium | Med Hi | Med Hi
| Unlikely | Low | Low Med | Low Med | Medium | Med Hi |  | Unlikely | Low | Low Med | Low Med | Medium | Med Hi
| Remote | Low | Low | Low Med | Medium | Medium |  | Remote | Low | Low | Low Med | Medium | Medium
|  | Insignificant | Minor | Moderate | Major | Critical |  |  | Insignificant | Minor | Moderate | Major | Critical
|  |  |  | Impact | [6 empty] | Impact